## Current
Set a Start date
2020-03-17
|  |  | Est | Est Task
| Title / Name of task | Notes: | Days work | Completion | Sum days work
| Reveiew and refactor Naming & function locations. |  | 2 | 2020-03-19 | 2
Code review for naming & correctness
Review missing common code that was Declaration and not Function * roll this one up into the one above | Review functional additions made to the MarketPlace Framework
| Research Reporting |  | 1 | 2020-03-20 | 3
Discuss reporting with market place engr < 1hr
Review report code of MktPlace: Determine code to pull in
| Develop exhaustive unit test, expose framework functions, run Reports |  | 5 | 2020-03-27 | 8
Implement Reporting framework
Moved form 1st block and combined with task from this block | Develop a workflow Unit test access every framework function
Write any necessary scripting to generate test results for reporting
| Implement new framework structure: decouple Frame from App |  | 3 | 2020-04-01 | 11
Move control and utils into Framework directory, refactor paths
Execute a full suite of tests
Fix bugs and retest until no fails
| At this point we would be functionally at JavaScript Framework Ver 1.0 | Ready for general consumption
Lower priority work : Feel it is important
| but not critical to delivering V1.0 | Additional Work
Start
| A date value cell under "Start" will calculate additional end dates | 2020-04-08
| Trace Logging : functionality that will be supportive |  | 6 | 2020-04-16 | 17
Finish the investigation of log4Js
Implement Logging level "TraceLog" : control from config files
apply logging to OpenApplication.doIt, ViewPort.scrollToBottom, scrollToTop ( cus I know at this time I am accurately hitting these functions) | Apply logging to known Frame Modules
Run all tests with TraceLog enabled: Evaluate results
| For future consideration |  | 2 | 2020-04-20 | 19
evaluate scripting necessary to execute small ESS app start
evaluate scripting necessary to execute small PD app start
Formulas:
Completion = D2+[Days work]
Completion = WORKDAY.INTL(F5,[Days work])

## Previous
Title / Name of task | Duration | summ of duration | Level of Importance
Review to this point | 3 days | 3 | 1
Reveiw the current Utils code for improved Naming
Review missing common code that was Declaration and not Function
Evaluate other current common.js looking for other pertinent common code
Implement a simplest possible walk through to payment selection. 1/2 day at most
Review test report structure of MktPlac
Research Reporting | 3 Days | 6 | 1
Discuss reporting with market place engr
Evaluate code necessary to pull in
Create a reporting branch off of Distill, "DistillReporting"
start report codeing and testing in DistillReporting branch
When Reporting is mature, merge back into Distillation
Expand Unit Test Runs to generate rpt data | 2 Days | 8 | 1
Discuss with mkt place some testing approaches
Work up additional scripting to gen test data more than is there now
Trace Logging | 4 - 6 Days | 15 | 2
Create a new branch off of Distillation for TraceLoggin
Finish the investigation of log4Js
dev some POC code to evaluate ability to implement general logging into new log files
Implement the TraceLogging Boolean and connect to new traceLoggin Files
apply logging to OpenApplication.doIt, ViewPort.scrollToBottom, scrollToTop ( cus I know at this time I am accurately hitting these functions)
Run my ./go A¦D¦C unit tests with TraceLog enabled: Evaluate results
Merge TraceLoggin back into Distillation
Push to repo and tag as version 0.75 with appropirate comment
Build out the new project structure decoupling Frame from App specific code | 3 Days | 11 | 1
Create a new branch off of Distillation
Move control and utils into Framework.
Execute a full suite of tests
Fix bugs and retest until no fails
Merge back into Distillation when confident of successful execution
Push to repo and tag as version 1.0 with appropriate comment
For future consideration | 2 Days | 17 | 2
evaluate scripting necessary to execute small ESS app start
evaluate scripting necessary to execute small PD app start