## initial PLan
Title / Name of task | Duration | summ of duration | Level of Importance
Review to this point | 3 days | 3 | 1
Reveiw the current Utils code for improved Naming
Review missing common code that was Declaration and not Function
Evaluate other current common.js looking for other pertinent common code
Implement a simplest possible walk through to payment selection. 1/2 day at most
Review test report structure of MktPlac
Research Reporting | 3 Days | 6 | 1
Discuss reporting with market place engr
Evaluate code necessary to pull in
Create a reporting branch off of Distill, "DistillReporting"
start report codeing and testing in DistillReporting branch
When Reporting is mature, merge back into Distillation
Expand Unit Test Runs to generate rpt data | 2 Days | 8 | 1
Discuss with mkt place some testing approaches
Work up additional scripting to gen test data more than is there now
Trace Logging | 4 - 6 Days | 15 | 2
Create a new branch off of Distillation for TraceLoggin
Finish the investigation of log4Js
dev some POC code to evaluate ability to implement general logging into new log files
Implement the TraceLogging Boolean and connect to new traceLoggin Files
apply logging to OpenApplication.doIt, ViewPort.scrollToBottom, scrollToTop ( cus I know at this time I am accurately hitting these functions)
Run my ./go A¦D¦C unit tests with TraceLog enabled: Evaluate results
Merge TraceLoggin back into Distillation
Push to repo and tag as version 0.75 with appropirate comment
Build out the new project structure decoupling Frame from App specific code | 3 Days | 11 | 1
Create a new branch off of Distillation
Move control and utils into Framework.
Execute a full suite of tests
Fix bugs and retest until no fails
Merge back into Distillation when confident of successful execution
Push to repo and tag as version 1.0 with appropriate comment
For future consideration | 2 Days | 17 | 2
evaluate scripting necessary to execute small ESS app start
evaluate scripting necessary to execute small PD app start

## Adopted Plan
Set a Start date
2020-03-17
|  |  | Est | Est Task
| Title / Name of task | Notes: | Days work | Completion | Sum days work
| Reveiew and refactor Naming & function locations. |  | 3 | 2020-03-20 | 3
Code review for naming & correctness
Review missing common code that was Declaration and not Function * roll this one up into the one above | Review functional additions made to the MarketPlace Framework
Documentation: Develop a flexible layout: initially cover core config and function purpose
| Research Reporting |  | 2 | 2020-03-24 | 5
Discuss reporting with market place engr < 1hr
Review report code of MktPlace: Determine code to pull in
Documentation: Add reporting technology
| Develop exhaustive unit test, expose framework functions, run Reports |  | 5 | 2020-03-31 | 10
Implement Reporting framework
Moved form 1st block and combined with task from this block | Develop a workflow Unit test access every framework function
Write any necessary scripting to generate test results for reporting
Minimally add appropriate documentations
| Implement new framework structure: decouple Frame from App |  | 4 | 2020-04-06 | 14
Move control and utils into Framework directory, refactor paths
Execute a full suite of tests
Fix bugs and retest until no fails
Document strucural change seperating Frame from App specific code.
| At this point we would be functionally at JavaScript Framework Ver 1.0 | Ready for general consumption
Lower priority work : Feel it is important
| but not critical to delivering V1.0 | Additional Work
Start
| A date value cell under "Start" will calculate additional end dates | 2020-04-07
| Trace Logging : functionality that will be supportive |  | 6 | 2020-04-15 | 20
Finish the investigation of log4Js
Implement Logging level "TraceLog" : control from config files
apply logging to OpenApplication.doIt, ViewPort.scrollToBottom, scrollToTop ( cus I know at this time I am accurately hitting these functions) | Apply logging to known Frame Modules
Run all tests with TraceLog enabled: Evaluate results
| For future consideration |  | 3 | 2020-04-20 | 23
evaluate scripting necessary to execute small ESS app start
evaluate scripting necessary to execute small PD app start
Formulas:
Completion = WORKDAY.INTL(D2,[Days work])
Completion = WORKDAY.INTL(F5,[Days work])

## Current State
Set a Start date
2020-03-17
|  |  | Est | Est Task | Status
| Title / Name of task | Notes: | Days work | Completion |  | Sum days work
| Research Reporting |  | 3 | 2020-03-20 |  | 3
Code review for naming & correctness
Discuss reporting with market place engr < 1hr
Review report code of MktPlace: Determine code to pull in
Documentation: Add reporting technology
| Implement Reporting framework |  |  |  | Done
| Reveiew and refactor Naming & function locations. |  | 2 | 2020-03-24 |  | 5
Review functional additions made to the MarketPlace Framework
| Documentation: Develop a flexible layout: initially cover core config and function purpose |  |  |  | Done
| Develop exhaustive unit test, expose framework functions, run Reports |  | 5 | 2020-03-31 |  | 10
Moved form 1st block and combined with task from this block | Develop a workflow Unit test access every framework function
Write any necessary scripting to generate test results for reporting
| Minimally add appropriate documentations |  |  |  | Done
| Implement new framework structure: decouple Frame from App |  | 4 | 2020-04-06 |  | 14
Move control and utils into Framework directory, refactor paths
Execute a full suite of tests
Fix bugs and retest until no fails
| Document strucural change seperating Frame from App specific code. |  |  |  | Done
| At this point we would be functionally at JavaScript Framework Ver 1.0 | Ready for general consumption
Lower priority work : Feel it is important
| but not critical to delivering V1.0 | Additional Work
Start
| A date value cell under "Start" will calculate additional end dates | 2020-04-07
| Trace Logging : functionality that will be supportive |  | 6 | 2020-04-15 |  | 20
| Finish the investigation of log4Js |  |  |  | Done
| Implement Logging level "TraceLog" : control from config files |  |  |  | 50% done
apply logging to OpenApplication.doIt, ViewPort.scrollToBottom, scrollToTop ( cus I know at this time I am accurately hitting these functions) | Apply logging to known Frame Modules
Run all tests with TraceLog enabled: Evaluate results
| For future consideration |  | 3 | 2020-04-20 |  | 23
evaluate scripting necessary to execute small ESS app start
evaluate scripting necessary to execute small PD app start
Formulas:
Est Task = WORKDAY.INTL(D2,[Est])
Est Task = WORKDAY.INTL(F5,[Est])

## Accomplishment
| Identified work completed | Identified work that needs attention | Recommended changes across the JS Frame user base
2020-03-24 | Tuesday March 24 2020
Following a constructive call with CU
Reviewed the nature of the two functions in Ramdom.js randomNo and randomTestVal()
RandomNo was found un used throughout the entire product test environment. I deprecated randonNo by commenting out.
RandomTestVal is in the proces of being refactored and new functions are being reconnected to previous calling locations. New fuctions are atomic and somewhat less error prone to call.
New functions are randomTestSTRING(n); requires length of string to return randomTestDATE(); no argument
randomeTestSTRING function has at least one unit test / functional test implemented via a call from pageTest\getAQuote\delta\basicPlus.test.js line 93 in function it('Unit Test: Access Random.js.randomTestSTRING ', function() Additionally pageObject\dependent-page.js also maks calls to randomeTestSTRING at lines 351&352
Lastly, all current Framework Unit tests run and pass without error
| 2020-03-27 | 2020-03-25 | 2020-03-27
| The following two files and managed functions Dates GetDatePart only called by a function that is not used at all getFullDate was not called by anything Files readPDFFiles is no longer used in any JS framework renameReports while there are two calls in the ESS Test framework. Since I am not forcing any frame to adopt the new core ESS Can for the time being continue useing renameReports as it it. | It looks like I should implement something like pageTests\dependents\delta\basic.test.js .. The deal is that there is a great deal of work just to have a position for adding dependents with CHILDDOB , the newest Random.js function. Will consider other alternatives like a page that already exist that needs just a little help getting there. | At some point in the near future the ESS framwork need to have the Cole/MarketPlace/Core Test Reporting frame work adopted.
| 3/27/2020 Moving logInfoPromise to ViewPort.js from Errors. Errors.js was an arbitrary place when deprecating common.js So, ViewPort.js is just as reasonable from that stand point. But more to how the function is used via lexical Scope use of 'this' and not thorough a Global Variable like Uitlity was used for, logInfoPromise belong in the same file that calles it. | 3/30/2020 I believe there is a snag in the reporting framework. When I run ./go 3 and run three suites in parallel I get one output folder , I get three json file, but only one report. The json files are named by the process id running. I'm looking at the methodology for reporting to determine if I can get it to gen the html for all json generated.
3/30/2020 it turns out that using the end to end framework to access all pages just requires too much of the Applicaiotn specific code into what I want to be just frame work. So, my ability to unit test Core functions by navigating over application pages will not keep the core clean. So, I will have to use the Jasmine methodology to unit test core code.