## V1
| Title / Name of task | Notes: |  | Days work | Completion | Sum days work
Initial Investigation POC / Protractor UI
| UI / Protractor configuration ( read not Jasmine REST API ) |  |  |  | Done
| * determine initial pass at sw and node packages needed |  |  |  | Done
| * Frisby, jasmine-data-provider, Log4js, Moment, Protractor, ssn |  |  |  | Done
| * configure local frame package and test that configuration out |  |  |  | Done
| Repeat the process and tests |  |  |  | Done
| Perform the same installation steps and test |  |  |  | Done
Finish Initial POC configuration
| * Resolve the jasmine-spec-reporter-cust undefined property BUG | BUG | Must have resolution | 1.5 |  | 1.5 | Dependency ?
| * Resolve the Log4Js Logger BUG | BUG | Must have resolution | 1.5 |  | 3 | Dependency ?
Resolve outstanding packaging to Artifactory
| Finish the FrameAsPackage Pipeline configuration | Started |  | Jason |  | Jason
| Incorporate Published FrameAsPackage |  |  | 3 |  | 6
| * resolve build failures on dd-FrAsPkgPipeLineTest * transfer FrAsPkgPipeLineTest config to dd-FrameAsPackage * Jenkins job must build and not fail. It uploads package to Artifactory | any config or work done here could simply be transferred to dd-FrameAsPackage and finished there
| Packaging(not node moduld )the upper level Project , deploy and test |  |  | 2 |  | 8
add gitignore or modify existing
add element-finder-extensions.js
add package.json
add protractor.conf.js
add jasmine.conf.js
| add description_code ( previously in the integration directory ) | App specific
Add README
'/===============================================================================================================================================
Upper project configuration Jasmine REST Api
| FrameAsPackage configuration for Jasmine REST API |  |  | 2 |  | 10
* How much frameAsPackage is needed ???
* The reporting module utils/htmlReporter
* the zephyr reporting module utils/ZephyrReporter
* runtime Config utility utils/configUtil.js
* Common fcns utils/common.js
* Custom matchers utils/custom_matcher.js
* Jasmine-spec-reporter
| Test |  |  | 3 |  | 13
| Node Modules necessary at the project level Modules needed at the project level complicates the simplicity of FrameAsPackage | I've written this section out because there are unknows here. I haven'd dug into this configuration yet. The fact that 3 packages are already needed by Protractor means only 3+ will be added to the package.json. Installation of these packages needs to be done with a small shell script so that we know it gets done. this would be done for both jasmine and protractor
frisby Already required by Protractor
jasmine-data-provider Already required by Protractor
moment Already required by Protractor
Jasmine
| jasmine-reporters ? Defined but I don't see called anywhere | Questionable | Not called in config
assert
qs
jasmine-spec-reporter req by FrameAsPackage Might be able to use

## V2
Title / Name of task | Notes: |  | Days work | Completion | Sum days work
Initial Investigation POC / Protractor UI
UI / Protractor configuration ( read not Jasmine REST API ) |  |  |  | Done
* determine initial pass at sw and node packages needed |  |  |  | Done
* Frisby, jasmine-data-provider, Log4js, Moment, Protractor, ssn |  |  |  | Done
* configure local frame package and test that configuration out |  |  |  | Done
Repeat the process and tests |  |  |  | Done
Perform the same installation steps and test |  |  |  | Done
Upper project configuration Jasmine REST Api
FrameAsPackage configuration for Jasmine REST API |  |  | 2 | 2020-08-21 | 2
Packaging(not node moduld )the upper level Project , deploy and test |  |  | 2 | 2020-08-25 | 4
Finish Initial POC configuration
* Resolve the jasmine-spec-reporter-cust undefined property BUG | BUG | Must have resolution | 1.5 | 8/26+/2020 | 5.5
* Resolve the Log4Js Logger BUG | BUG | Must have resolution | 1.5 | 2020-08-28 | 7
Resolve outstanding packaging to Artifactory
Finish the FrameAsPackage Pipeline configuration | Started |  | Jason |  | Jason
Incorporate Published FrameAsPackage |  |  | 3 | 2020-09-02 | 10
* resolve build failures on dd-FrAsPkgPipeLineTest * transfer FrAsPkgPipeLineTest config to dd-FrameAsPackage * Jenkins job must build and not fail. It uploads package to Artifactory | any config or work done here could simply be transferred to dd-FrameAsPackage and finished there
TEST |  |  | 3 | 2020-09-09 | 13